## Project Details
Project Detail
Project Name | orangehrmlive | Browser Version | 130.0.6723.58
Module Name | Login Page | Build No. | 1.0.0
Assign Date | 2024-04-03 | Cross Browser Testing | Chrome ¦ Edge
Assign By | TL
Sprint | 2024-04-05

## Decision Table
Decision Table
Fields | Tc1 | Tc2 | Tc3 | Tc4 | Tc5 | Tc6 | Tc7 | Tc8 | Tc9 | Login Credentials
Username | Valid | Invalid | Valid | Invalid | Valid | B | Invalid | B | B | Admin
Password | Valid | Valid | Invalid | Invalid | B | Valid | B | Invalid | B | admin123
Outcomes | V | IN | IN | IN | IN | IN | IN | IN | IN | V

## Test Scenario
Test Scenario (Orange hrm live)
SR No | Test Scenario ID | Test Scenario Title | Reference | Total no of Test Cases
1 | TS_01 (Login Page) | To Verify User able To Test Login Page | SRS | 9
2 | TS_02 (Register Page) | To Verify User able To Test Register Page | SRS | 17
3
4
5

## Test Cases
Test Cases (Orange hrm live)
SR No | Test Case ID | Test Scenario ID | Test Scenario Title | Test Case Title | Pre Condition | Test Steps | Test Data | Actual Result | Expected Result | Status
1 | TC_01 (Login Page) | TS_01 (Login Page) | To Verify User able To Test Login Page | Validate If A User Will Be Able To Login With A Valid Username And Valid Password |  | 1: Open Chrome Browser 2: Enter URL 3: Enter Valid Username 4: Enter Valid Password 5: Click on Login Button | 1: Enter URL = "https://opensource- demo.orangehrmlive.com/web/ind ex.php/auth/login" 2: Valid Username = "Admin" 3: Valid Password = "admin123" | Login Successful | Should Be Logged-In Successfully | Pass
2 | TC_02 (Login Page) | TS_01 (Login Page) | To Verify User able To Test Login Page | Validate If A User Will Be Able To Login With A Valid Username And Invalid Password |  | 1: Open Chrome Browser 2: Enter URL 3: Enter Valid Username 4: Enter Invalid Password 5: Click on Login Button | 1: Enter URL = "https://opensource- demo.orangehrmlive.com/web/ind ex.php/auth/login" 2: Valid Username = "Admin" 3: Valid Password = "admin12345" | Login Unsuccessful | Should Not Be Logged-In Successfully | Pass

## Bug Report
Bug Report
Bug ID | BUG-001
Reported By: | Siddhant Jain
Date | 2025-11-21
Severity | Medium
Priority | Medium
Description | Login page allows login with invalid credentials without error message.
Steps to Reproduce:
1. Navigate to the OrangeHRM Demo Website.
2. Enter an invalid username in the 'Username' field.
3. Enter an incorrect password in the 'Password' field. |  |  | admin123
4. Click the 'Login' button.
Expected Result:
A clear error message should be displayed, indicating that the credentials are invalid.
Actual Result:
No error message appears, and the user remains on the login page.
Test Data:
Username: | admin instead of Admin
Password: | admin123
Environment:
Browser: [Browser Name, Version]
Operating System: [OS Name, Version]

## Test Execution Summary
Test Execution Summary
Project Name: OrangeHRM Login Testing
Module: Login Page
Testing Type: Manual Testing
Test Period: [Start Date] to [End Date]
Test Environment: Browser-based testing on [Windows / MacOS]
Test Case Summary
Total Test Cases Executed: [Total Number of Test Cases Executed]
Test Cases Passed: [Number of Test Cases Passed]
Test Cases Failed: [Number of Test Cases Failed]
Test Cases Blocked: [Number of Test Cases Blocked, if any]
Test Cases Not Executed: [Number of Test Cases Not Executed, if any]
Key Findings
Critical Bugs: [Number of Critical Bugs Found]
High Priority Bugs: [Number of High Priority Bugs Found]
Medium Priority Bugs: [Number of Medium Priority Bugs Found]
Low Priority Bugs: [Number of Low Priority Bugs Found]
Overall Outcome
Pass Rate: [Percentage of Passed Test Cases]
Fail Rate: [Percentage of Failed Test Cases]
Defects Identified: [Total Number of Bugs Reported]
Observations and Recommendations
1. The login functionality worked as expected for valid inputs, ensuring successful authentication.
2. Observed inconsistencies in error message display for invalid login attempts. Suggested improvement: uniform error handling.